## Master Scope
SN | Phase | Module | Feature Name | Feature Description (Client-Friendly) | User Roles | Platform | Backend Dependency (Yes/Partial/No) | Complexity (Low/Medium/High) | Assumptions | Explicit Exclusions | Risk Note | Effort (Person-Days) | Est. Hours | Cost | Notes / Negotiation Buffer
| 🟦 PHASE 0 — FOUNDATION, ARCHITECTURE & INTEGRATION | [14 empty] | Hourly Rate
| Goal | Stand up the app skeleton, managed backend, security model, and the BLE lock/unlock interface specification before any feature work begins. This phase locks the architecture, hands a clear BLE protocol to the client's firmware team, and gets the app building on both iOS and Android.
| Client framing: | • Full system architecture and data-flow design across app, backend, and BLE device • BLE Interface Spec (lock/unlock + dead-man auto-lock) delivered to the firmware team • Managed backend (BaaS): authentication, user/device database, and push set up • React Native app scaffold building on both iOS and Android via CI/CD • Privacy-by-design security model — on-device data handling, secure storage, encryption • Design system / UI kit and key-screen wireframes
1 | Phase 0 | Architecture | System Architecture & Data-Flow Design | Define the full app–backend–BLE-device architecture, including data-flow diagrams, the privacy-by-design model (no raw ID/biometric data leaves the device), and the integration blueprint for all later phases. | All | Mobile + Backend | Yes | High | Client confirms BaaS choice (Supabase/Firebase) and device hardware (YC1012_JD). | Infrastructure procurement / hosting | Architecture gaps discovered late once firmware constraints are known. | 3 | 24 |  | Architecture must be approved before Phase 1 begins.
2 | Phase 0 | BLE | BLE Interface Spec (Lock/Unlock + Dead-Man Auto-Lock) | Author the custom GATT service contract for the firmware team: lockState (read/notify), lockCommand (authenticated write), and auth/session pairing token, plus the firmware-side auto-lock-on-disconnect behaviour. | All | Backend | Yes | High | Firmware team will implement to our spec and is available for review. | Firmware development on the device itself | Spec ambiguity causing firmware/app mismatch at integration. | 3 | 24 |  | This spec is the contract for Phase 3 joint integration testing.
3 | Phase 0 | Backend | BaaS Setup — Auth, DB Schema & Push | Provision the managed backend: authentication, the users/devices/verification-flag database schema, and push (FCM/APNs). Backend stores only an age_verified boolean + timestamp/method — never raw documents or biometrics. | Admin | Backend | Yes | Medium | Client provides or approves the BaaS account and billing. | Self-hosted backend infrastructure | Vendor limits or quota on auth/push at scale. | 2 | 16 |  | Single source of truth for accounts and device ownership.
4 | Phase 0 | App | RN App Scaffold, Navigation & Native Module Wiring | Set up the React Native + TypeScript project, navigation structure, and wiring for native modules: BLE (react-native-ble-plx), camera (vision-camera), on-device ML, and secure storage (Keychain/Keystore). | All | Mobile (iOS+Android) | Partial | Medium | Single shared codebase targeting current iOS and Android versions. | Native OS-specific custom UI beyond agreed screens | Native module incompatibilities across RN versions. | 2.5 | 20 |  | Foundation all feature phases build on.
5 | Phase 0 | DevOps | CI/CD + Dev / Staging / Prod Build Pipelines | Configure Development, Staging, and Production environments with automated iOS and Android build, signing, and deployment pipelines (TestFlight / Play Internal Testing for staging builds). | Admin | Backend | No | Medium | Client provides Apple and Google developer accounts and signing assets. | Ongoing hosting / account cost management | Code-signing and provisioning friction, especially iOS. | 2.5 | 20 |  | Staging must mirror production configuration.
6 | Phase 0 | Security | Privacy & Security Design (On-Device Handling, Secure Storage, Encryption) | Design the security model: on-device-only processing of ID/selfie/biometrics, encrypted secure storage of tokens, HTTPS everywhere, and the deletion policy that runs after each verification decision. | All | Mobile + Backend | Partial | High | On-device ML is sufficient for the verification flow (no KYC vendor). | Third-party / government ID validation APIs | Mishandling of sensitive data if deletion policy is incomplete. | 2 | 16 |  | Privacy-by-design is a core selling point — must be airtight.
7 | Phase 0 | Design | Design System / UI Kit + Key-Screen Wireframes | Produce the design system (colour, type, components) and wireframes for key screens: onboarding, device pairing, age verification flow, and lock/unlock control. | All | Mobile (iOS+Android) | No | Medium | Brand assets (logo, palette) provided by client or agreed early. | Full high-fidelity design for add-on / admin screens | Design churn if key flows change after wireframe sign-off. | 3 | 24 |  | Design is front-loaded so build can start in week 1–2.
[11 empty] | Total Working Days | 18 | 144 | 0
| Exit Criteria | - System architecture document approved by all stakeholders
- BLE Interface Spec delivered to and acknowledged by the firmware team
- Backend auth and database live; age_verified flag schema in place
- App builds and runs on both iOS and Android via CI/CD
- Dev / Staging / Production environments configured
- Design system and key-screen wireframes approved
🟩 PHASE 1 — ACCOUNTS & DEVICE MANAGEMENT (BLE)
| Goal | Deliver the full account lifecycle and the ability to pair and manage multiple BLE devices. By the end of this phase a user can register, sign in, discover and bond devices, and see live device status that survives reconnects and app backgrounding.
| Client framing | • Signup, login, and password reset via the managed backend • Onboarding flow with BLE and camera permission handling • BLE device scan, discovery, and secure pairing / bonding • Multi-device management — list, rename, unpair, status, battery • Device-to-account sync so ownership is enforced server-side • Robust connection lifecycle: reconnect and background handling
1 | Phase 1 | Auth | Signup / Login / Password Reset | Account creation, secure login, and email-based password reset handled by the managed backend (BaaS). Establishes the verified identity that device ownership and age status attach to. | Customer | Mobile (iOS+Android) | Yes | Medium | BaaS auth supports email/password and reset email flow. | Social / SSO login | Email deliverability for reset links. | 2.5 | 20
2 | Phase 1 | Onboarding | Onboarding & Permissions (BLE, Camera) Flow | Guided first-run experience that explains the app and requests BLE and camera permissions at the right moment, with clear fallback messaging if a permission is denied. | Customer | Mobile (iOS+Android) | No | Low | Standard OS permission dialogs are acceptable to client. | Custom permission-priming screens beyond agreed flow | Users denying permissions and getting stuck — needs recovery path. | 1.5 | 12
3 | Phase 1 | BLE | Device Scan & Discovery | Scan for nearby Blue Smoke devices over BLE and present discoverable devices to the user for selection, filtering to the project's GATT service. | Customer | Mobile (iOS+Android) | Partial | Medium | Device advertises the agreed BLE service UUID. | Support for non-Blue-Smoke BLE peripherals | Scan reliability differences across Android OEMs. | 2.25 | 18
4 | Phase 1 | BLE | Pairing / Bonding Flow | Secure BLE bonding plus an app-level device token bound to the verified account, so only the bonded, verified user's app can later command the device. | Customer | Mobile (iOS+Android) | Yes | High | Firmware supports BLE bonding and token exchange per spec. | Out-of-band / NFC pairing | Bonding edge cases and lost-bond recovery. | 3 | 24 |  | Pairing security underpins all lock/unlock authority.
5 | Phase 1 | Devices | Multi-Device Management (List, Rename, Unpair, Status, Battery) | Manage multiple paired devices: list all bonded devices, rename them, unpair, and view live connection status and battery level for each. | Customer | Mobile (iOS+Android) | Yes | Medium | Device exposes battery via the lockState characteristic. | Sharing a device across multiple accounts | Status/battery polling impact on battery and connection. | 3 | 24
6 | Phase 1 | Sync | Device ↔ Account Sync to Backend | Sync paired-device records to the backend so device ownership is enforced server-side and survives reinstalls and new devices. | Customer | Backend | Yes | Medium | Backend device model defined in Phase 0. | Cross-user device transfer workflow | Sync conflicts when the same device is re-paired elsewhere. | 2 | 16
7 | Phase 1 | BLE | Connection Lifecycle (Reconnect, Background Handling) | Manage the BLE connection across app states: automatic reconnect after drops and correct behaviour when the app is backgrounded or relaunched. | Customer | Mobile (iOS+Android) | Partial | High | Target OS versions allow the required background BLE modes. | Guaranteed connectivity in OS-killed / terminated state | iOS background BLE restrictions are a known hard problem. | 3 | 24 |  | De-risked further in Phase 3 background work.
8 | Phase 1 | Profile | Profile & Settings | User profile and app settings: view account details, manage notification preferences, and access support/legal links. | Customer | Mobile (iOS+Android) | Partial | Low | Profile fields limited to agreed set. | In-app account deletion / data-export tooling |  | 1.5 | 12
[10 empty] | Total Working Day |  | 18.75 | 150 | 0
| Exit Criteria | - User can sign up, sign in, and reset password
- User can scan, pair, and bond multiple devices
- Devices can be listed, renamed, and unpaired
- Live device status and battery shown per device
- Connection reconnects correctly across app foreground/background states
🟨 PHASE 2 — AGE & IDENTITY VERIFICATION (ON-DEVICE)
| Goal | Deliver the 18+ gate entirely on-device: government-ID OCR for date of birth plus a selfie-vs-ID face match, with no third-party KYC vendor and no raw data leaving the phone. This is the highest-risk phase and includes dedicated accuracy-tuning time.
| Client framing | • Guided ID capture with edge detection • On-device OCR + DOB extraction (text recognition and PDF417/MRZ barcode) • 18+ age computation handling multiple DOB formats • Selfie capture with basic liveness, Face-ID-enrollment style • ID-photo vs selfie face match with tuned similarity threshold • Retry, failure, and manual-fallback policy for legitimate edge cases • Secure deletion of ID/selfie/biometrics after the pass/fail decision
1 | Phase 2 | Capture | Guided ID Capture UI (Edge Detection) | Camera UI that guides the user to photograph a government ID, with edge detection and quality checks to capture a clean, readable image for OCR. | Customer | Mobile (iOS+Android) | No | Medium | Physical sample government IDs available for testing. | Supporting every international ID format | Poor lighting / glare reducing capture quality. | 2.3 | 18
2 | Phase 2 | OCR | ID OCR + DOB Extraction (Text + PDF417 / MRZ) | On-device text recognition (ML Kit / Apple Vision) plus PDF417/MRZ barcode parsing to reliably extract date of birth from the captured ID. | Customer | Mobile (iOS+Android) | No | High | Target IDs carry DOB in readable text and/or barcode. | Cloud OCR services | DOB extraction accuracy across ID layouts and old IDs. | 4.8 | 38 |  | On-device only — no document leaves the phone.
3 | Phase 2 | Age | Age (18+) Computation & Multi-Format DOB Rules | Normalise the extracted DOB across date formats, compute age, and enforce the 18+ requirement as a hard gate. | Customer | Mobile (iOS+Android) | No | Medium | 18+ threshold confirmed with client. | Region-specific minimum-age variations | Date-format ambiguity (e.g. MM/DD vs DD/MM). | 2 | 16 |  | Threshold is configurable if client needs 21+ in some regions.
4 | Phase 2 | Selfie | Selfie Capture with Liveness (Face-ID Style) | Guided selfie capture with basic liveness detection (blink/turn/multi-frame) to confirm a live person is present before face matching. | Customer | Mobile (iOS+Android) | No | High | Device front cameras meet a baseline quality bar. | Advanced anti-spoofing / presentation-attack detection | Liveness false rejects on lower-end devices. | 3.3 | 26 |  | Advanced anti-spoofing available as an add-on.
5 | Phase 2 | Face Match | ID-Photo vs Selfie Face Match + Threshold Tuning | Extract face embeddings from the ID photo and the selfie, compare similarity against a tuned threshold, and decide a match — fully on-device. Includes dedicated tuning time. | Customer | Mobile (iOS+Android) | No | High | On-device face embedding models are sufficiently accurate. | Server-side / vendor biometric matching | False rejects from poor ID photos — the single biggest accuracy risk. | 5 | 40 |  | Largest line item by design — accuracy tuning is critical.
6 | Phase 2 | Flow | Result Handling, Retries, Failure States & Manual Fallback Policy | Orchestrate the end-to-end decision: pass requires (age ≥ 18) AND (face match ≥ threshold). Handle retries, clear error states, and an agreed manual-review fallback for legitimate edge cases. | Customer / Admin | Mobile (iOS+Android) | Partial | Medium | Manual fallback policy (e.g. support contact) agreed with client. | Automated human review queue / back-office tooling | Edge-case users blocked with no recourse if fallback undefined. | 2.3 | 18 |  | Manual fallback policy must be agreed before build.
7 | Phase 2 | Privacy | Secure Handling + Deletion of ID / Selfie / Biometrics | Process all images and embeddings in memory / secure storage and delete them immediately after the pass/fail decision. Backend receives only the age_verified flag plus timestamp/method. | Customer | Mobile + Backend | Partial | Medium | Security design from Phase 0 finalised. | Retaining ID/selfie for audit | Incomplete deletion leaving sensitive data on device. | 2 | 16 |  | No raw documents or biometrics are ever stored or transmitted.
8 | Phase 2 | Gating | Verification Status Persisted; Gates First Activation | Persist the verified status and use it to gate first-time device activation — an unverified user cannot activate or unlock any device. | Customer | Mobile + Backend | Yes | Low | age_verified flag schema available from Phase 0. | Re-verification scheduling / expiry policy | Flag tampering if not validated server-side. | 1.5 | 12
[10 empty] | Total Working Day |  | 23.2 | 184 | 0
| Exit Criteria | - Valid 18+ ID with a matching selfie results in a pass
- Under-18 ID or mismatched selfie is blocked
- DOB extracted correctly across supported ID formats
- Images and biometrics deleted after the decision
- Backend stores only the age_verified flag (+ timestamp/method)
- First device activation is gated on verification
🟥 PHASE 3 — PROXIMITY LOCK/UNLOCK & PRODUCTION HARDENING
| Goal | Deliver secure, authenticated lock/unlock plus proximity auto-lock, prove it against real firmware, and harden the app for store launch. The device auto-locks itself when the phone leaves BLE range; the app is the controller and never relies on the phone alone to keep the device locked.
| Client framing | • First-time unlock (post-verification activation) • Authenticated lock/unlock via the BLE characteristic • Proximity monitor (RSSI/connection) with auto-lock on range loss • Background BLE behaviour on iOS and Android — auto-lock when out of range • Push notifications for lock status and low battery • Joint firmware integration testing on a real device • End-to-end QA, security review, and dual app-store submission
1 | Phase 3 | Activation | First-Time Unlock (Post-Verification Activation) | Activate a device for the first time only after age verification has passed, transitioning it from locked-by-default to a usable state for the verified owner. | Customer | Mobile (iOS+Android) | Yes | Medium | Verification gating from Phase 2 in place. | Activation without verification | Activation race conditions on first connect. | 2 | 16
2 | Phase 3 | Control | Lock/Unlock via BLE Characteristic (Authenticated) | Send authenticated lock and unlock commands to the device over the BLE lockCommand characteristic, validated by the pairing token so only the bonded, verified user can command it. | Customer | Mobile (iOS+Android) | Yes | High | Firmware implements authenticated lockCommand per spec. | Firmware-side command logic (client team) | Auth/token edge cases allowing unintended commands. | 3 | 24 |  | Core safety control — exhaustively tested.
3 | Phase 3 | Proximity | Proximity Monitor (RSSI / Connection) + Auto-Lock on Range Loss | Continuously monitor signal strength and connection state; when the phone moves out of range the app issues an explicit lock, as a secondary signal to the firmware's own dead-man auto-lock. | Customer | Mobile (iOS+Android) | Partial | High | RSSI thresholds tunable to an agreed range behaviour. | Centimetre-accurate ranging | RSSI noise causing premature or missed auto-lock. | 4.75 | 38 |  | Works alongside firmware dead-man auto-lock, not instead of it.
4 | Phase 3 | Background | Background BLE Behaviour (iOS + Android, Auto-Lock Out of Range) | Ensure proximity auto-lock continues to work when the app is backgrounded on both platforms, within each OS's background BLE constraints. | Customer | Mobile (iOS+Android) | Partial | High | Required background BLE entitlements/modes are permitted. | Guaranteed behaviour when the OS fully terminates the app | Cross-platform background BLE differences, especially iOS. | 4 | 32 |  | One of the two known hard problems — early spikes planned.
5 | Phase 3 | Push | Push Notifications (Lock Status, Low Battery) | Push notifications for key device events: lock/unlock status changes and low-battery alerts, delivered via FCM/APNs. | Customer | Mobile + Backend | Yes | Medium | Push infrastructure from Phase 0 live. | Marketing / promotional push campaigns | Delivery reliability when device events fire rapidly. | 2 | 16
6 | Phase 3 | Integration | Joint Firmware Integration Testing on Real Device | Test the app against real firmware on a physical device: pairing, authenticated lock/unlock, and firmware-side dead-man auto-lock, jointly with the client's firmware team. | All | Mobile (iOS+Android) | Yes | High | Physical device available by ~week 6 for integration. | Firmware development / fixes (client team) | Firmware readiness slipping past the integration window. | 3 | 24 |  | Mock peripheral used until firmware is ready.
7 | Phase 3 | QA | End-to-End QA, Edge Cases & Security Review | Full end-to-end QA across verification, pairing, lock/unlock, and proximity auto-lock, including edge cases and a security review before launch. | All | Mobile (iOS+Android) | No | High | Test matrix and devices agreed with client. | Formal third-party penetration test / certification | Late-surfacing edge cases delaying launch. | 3 | 24 |  | Security review precedes store submission.
8 | Phase 3 | Release | App Store Prep + Submission (iOS + Android) | Prepare store listings, assets, and compliance materials and submit to the Apple App Store and Google Play, including age-restriction / regulated-product review considerations. | Admin | Mobile (iOS+Android) | No | Medium | Client developer accounts and store assets ready. | Ongoing post-launch store management | Store review delays for an age-restricted product category. | 2 | 16 |  | Age-restricted category may draw extra store scrutiny.
[10 empty] | Total Working Day |  | 23.75 | 190 | 0
| Exit Criteria | - Verified user can lock and unlock the device in range
- Device auto-locks when the phone leaves BLE range (firmware + app)
- Auto-lock continues to work when the app is backgrounded
- Push notifications fire for lock status and low battery
- App passes end-to-end QA and security review
- App is live on both the App Store and Google Play
➕ ADD-ONS Included
| Goal | Optional modules quoted separately and not included in the core 4-phase delivery. Presented so the client can see the natural extensions of the platform and budget for them when ready.
| Client framing | • Admin web panel for device fleet, verification audit, and user management • Analytics and crash reporting (Firebase / Sentry) • Firmware development on the YC1012 / Cortex-M0+ (separate estimate) • Advanced liveness — anti-spoofing / presentation-attack detection
1 | Add-On | Admin | Admin Web Panel (Fleet, Verification Audit, User Management) | Web panel for administrators to view the device fleet, audit verification outcomes (pass/fail counts and methods, never raw biometrics), and manage users. | Admin | Web (Admin Panel) | Yes | High | Scope of admin actions agreed with client. | Included in base scope | Audit data must never expose raw ID/biometric material. | 15 | 120 |  | Significant standalone module — quoted separately.
2 | Add-On | Analytics | Analytics & Crash Reporting (Firebase / Sentry) | Integrate analytics and crash reporting to track adoption, drop-off in the verification funnel, and stability across devices. | Admin | Mobile + Backend | Partial | Medium | Client selects and provides analytics tooling accounts. | Custom BI dashboards | Analytics must respect the privacy-by-design model. | 3 | 24
| Exit Criteria | - Each add-on quoted and scheduled separately from core delivery
- Admin panel exposes audit metadata only — never raw biometrics
➕ ADD-ONS — OUT OF BASE SCOPE (Ideas)
| Goal | Optional modules quoted separately and not included in the core 4-phase delivery. Presented so the client can see the natural extensions of the platform and budget for them when ready.
| Client framing | • Admin web panel for device fleet, verification audit, and user management • Analytics and crash reporting (Firebase / Sentry) • Firmware development on the YC1012 / Cortex-M0+ (separate estimate) • Advanced liveness — anti-spoofing / presentation-attack detection
3 | Add-On | Firmware | Firmware Development (YC1012 / Cortex-M0+) | If the client wants us to build the device firmware (rather than only specifying the BLE protocol), this is scoped and estimated separately against the YC1012_JD / Cortex-M0+ target. | All | Firmware | Yes | High | Hardware, toolchain, and reference firmware access provided. | Included in base scope (base = spec only) | Hardware/firmware unknowns until toolchain access. | 0 | 0 |  | Separate estimate — effort TBD after hardware review.
4 | Add-On | Verification | Advanced Liveness (Anti-Spoofing / PAD) | Stronger presentation-attack detection on top of the base selfie liveness, to resist photo/video/mask spoofing attempts. | Customer | Mobile (iOS+Android) | No | High | Acceptable accuracy/UX trade-off agreed with client. | Included in base scope | Anti-spoofing increases false rejects if over-tuned. | 7.5 | 60 |  | Recommended if regulatory scrutiny is high.
| Exit Criteria | - Each add-on quoted and scheduled separately from core delivery
- Admin panel exposes audit metadata only — never raw biometrics
- Firmware development estimated after hardware/toolchain review