## Master Scope
BLUE SMOKE — Vape Device Control App — Master Scope & Work Breakdown
Hourly Rate (USD) | 25 |  | Platform: React Native (iOS+Android) · Verification: on-device ML · Backend: managed BaaS · Firmware: client team (to our spec)
SN | Phase | Module | Feature Name | Feature Description (Client-Friendly) | User Roles | Platform | Backend Dependency | Complexity | Assumptions | Explicit Exclusions | Risk Note | Effort (Person-Days) | Est. Hours | Cost | Notes / Negotiation Buffer
🟦 PHASE 0 — FOUNDATION, ARCHITECTURE & INTEGRATION
Goal | Establish the app skeleton, managed backend, security/privacy model, and the BLE interface specification (lock/unlock + dead-man auto-lock) that the client firmware team will implement — before any customer-facing feature work begins.
Client framing | This phase delivers: • Full system & data-flow architecture for app + BaaS + device • A BLE Interface Spec handed to the firmware team • Managed backend (auth, users, devices, verification flag, push) • React Native app scaffold + CI/CD for iOS & Android • Privacy & security design (all ID/biometric data stays on-device) • Design system and key-screen wireframes
1 | 0 | Architecture | System Architecture & Data-Flow Design | Define the full app–BaaS–device architecture: API contracts, data flow, on-device data handling, and integration blueprint for all phases | Admin | Backend | Yes | High | Device hardware (YC1012_JD + Cortex-M0+) specs available; BaaS chosen | Hosting/infra procurement | Hardware/BLE limitations discovered late |  | 24 |  | Architecture doc must be approved before Phase 1 begins
2 | 0 | BLE | BLE Interface Spec (Lock/Unlock + Auto-Lock) | Define the custom GATT service: lock/unlock characteristic, lock-state/battery notify, authenticated session token, and firmware-side dead-man auto-lock on link loss. Delivered as a spec doc for the firmware team | Admin | Both | Partial | High | Firmware team can implement the spec on the device SoC | Firmware development | Firmware team availability / implementation slippage |  | 24 |  | Hard dependency: firmware must implement this before Phase 3 integration
3 | 0 | Backend | BaaS Setup — Auth, DB Schema & Push | Provision managed backend (Supabase/Firebase): authentication, database schema (users, devices, verification flag, audit), and push (FCM/APNs) foundation | All | Backend | Yes | Medium | BaaS account available; schema agreed | Custom backend build | Vendor limits on auth/push |  | 16 |  | Stores only an age_verified flag — never raw ID/biometric data
4 | 0 | App | React Native App Scaffold & Native Modules | Set up the RN app: navigation, TypeScript config, state management, and wiring of native modules (BLE, camera, ML, secure storage) | All | Mobile | No | Medium | RN toolchain and native module libraries compatible | Native (Swift/Kotlin) rewrite | Native module version conflicts across platforms |  | 20 |  | Single codebase for iOS + Android
5 | 0 | DevOps | CI/CD & Environments (Dev/Staging/Prod) | Configure Dev/Staging/Prod environments and CI/CD pipelines with automated builds and signing for both iOS and Android | Admin | Both | No | Medium | Apple & Google developer accounts provided by client | Ongoing infra cost management | Signing/provisioning issues on iOS |  | 20 |  | TestFlight + Play Internal Testing used for demos
6 | 0 | Security | Privacy & Security Design | Design on-device data handling, encrypted secure storage (Keychain/Keystore), HTTPS, token handling, and the data-deletion policy for ID/selfie/biometrics | Admin | Both | Partial | High | SSL ready; secure storage APIs available | Penetration testing (flagged for Phase 3) | Misconfigured storage or key leakage |  | 16 |  | Privacy-by-design is a key client selling point
7 | 0 | Design | Design System & Key-Screen Wireframes | Build the UI kit (components, theme) and wireframe the key flows: onboarding, pairing, verification, lock/unlock | All | Mobile | No | Medium | Brand assets provided by client | Full marketing site design | Design iterations extend timeline |  | 24 |  | Front-loaded so engineering is never blocked on design
Subtotal
Exit Criteria | - System architecture document approved by all stakeholders - BLE Interface Spec delivered to and acknowledged by firmware team - Authentication and database live (users, devices, verification flag) - React Native app builds on both iOS and Android via CI/CD - Privacy/security design documented (on-device data, deletion policy) - Design system and key-screen wireframes approved
🟩 PHASE 1 — ACCOUNTS & DEVICE MANAGEMENT (BLE)
Goal | Enable users to create accounts, log in, and pair & manage multiple devices over Bluetooth Low Energy, with a reliable connection lifecycle across foreground and background.
Client framing | This phase delivers: • Account lifecycle: signup, login, password reset • BLE device scan, discovery, pairing and bonding • Multiple devices per account (list, rename, unpair, status, battery) • Device ↔ account sync • Robust connection lifecycle (reconnect, background) • Profile & settings
1 | 1 | Auth | Signup / Login / Password Reset | Account creation, login, and password reset via the managed backend. Secure session/token handling and logout | Customer | Mobile | Yes | Medium | BaaS auth supports email (and optional social) | SSO / enterprise identity | Token expiry/refresh edge cases |  | 20 |  | Session timeout to be agreed with client
2 | 1 | Onboarding | Onboarding & Permissions Flow | First-run onboarding that explains the product and requests Bluetooth and camera permissions with clear rationale | Customer | Mobile | No | Low | Standard OS permission flows | Animated/video onboarding | Permission denial handling UX |  | 12 |  | Permissions framed to maximise opt-in
3 | 1 | BLE | Device Scan & Discovery | Scan for nearby Blue Smoke devices over BLE and present discoverable devices to the user | Customer | Mobile | No | Medium | Device advertises a known service UUID | Non-BLE transports | Scanning behaviour differences across OS versions |  | 18 |  | Filter to Blue Smoke devices only
4 | 1 | BLE | Pairing / Bonding Flow | Pair and bond with a device, establish the authenticated session, and associate it with the user's account | Customer | Mobile | Partial | High | Firmware supports bonding + session token | Multi-user shared device | Bonding reliability across iOS/Android |  | 24 |  | Device token bound to the verified account
5 | 1 | Devices | Multi-Device Management | Manage multiple paired devices: list, rename, unpair, and view live status (connected/locked, battery) | Customer | Mobile | Yes | Medium | Backend stores device records per user | Device sharing between accounts | State sync conflicts across devices |  | 24 |  | A user can pair several devices
6 | 1 | Sync | Device ↔ Account Sync | Sync paired-device records and state between the app and backend so devices persist across reinstalls/logins | Customer | Both | Yes | Medium | Backend device model available | Cross-user device transfer | Sync lag / offline edits |  | 16 |  | Single source of truth in backend
7 | 1 | BLE | Connection Lifecycle & Reconnect | Handle connect/disconnect, automatic reconnect, and behaviour when the app is backgrounded or the phone sleeps | Customer | Mobile | No | High | OS background BLE modes available | Guaranteed always-on background scanning | iOS background BLE restrictions |  | 24 |  | Foundational for proximity auto-lock in Phase 3
8 | 1 | Profile | Profile & Settings | View account profile and app settings (notifications, paired devices, sign out) | Customer | Mobile | Partial | Low | Profile data in backend | In-depth account editing | — |  | 12 |  | Read-mostly; account edits minimal
Subtotal
Exit Criteria | - User can sign up, log in, and reset password - User can scan, pair, and bond with a device over BLE - User can pair multiple devices and see them listed - User can rename and unpair devices; live status and battery shown - Connection reconnects reliably across foreground/background - Device records persist via backend sync
🟨 PHASE 2 — AGE & IDENTITY VERIFICATION (ON-DEVICE)
Goal | Gate first-time device activation behind an on-device 18+ check: read date of birth from a government ID and match the ID photo against a live selfie — entirely on-device, with no third-party verification service. This is the highest-risk phase.
Client framing | This phase delivers: • Guided government-ID capture • On-device OCR to read date of birth and confirm 18+ • Guided selfie capture with basic liveness • On-device face match: ID photo vs selfie • Pass/fail decision with retries and a manual fallback policy • Secure handling and deletion of all images/biometrics • Verification status that gates first device activation ⚠️ No data leaves the device; only an age_verified flag is stored.
1 | 2 | Capture | Guided ID Capture UI | Camera UI with edge detection and guidance so the user can photograph their government ID clearly | Customer | Mobile | No | Medium | Device camera adequate; ML edge detection available | Hardware document scanners | Glare/low-light reduces capture quality |  | 18 |  | Quality of capture directly affects OCR + match accuracy
2 | 2 | OCR | ID OCR & DOB Extraction | On-device text recognition (and PDF417/MRZ barcode parsing where present) to extract the date of birth from the ID | Customer | Mobile | No | High | ML Kit (Android) / Vision (iOS) text & barcode APIs | Government ID validation / authenticity APIs | Varied ID layouts across regions reduce accuracy |  | 38 |  | We verify AGE only; supported ID types to be confirmed per market
3 | 2 | Age | Age (18+) Computation & DOB Rules | Parse extracted DOB across formats, compute age, and enforce the 18+ rule with clear pass/fail | Customer | Mobile | No | Medium | DOB reliably extracted by OCR step | ID expiry / fraud checks | Date format ambiguity (DD/MM vs MM/DD) |  | 16 |  | The only thing verified is age ≥ 18
4 | 2 | Selfie | Selfie Capture with Liveness | Guided, Face-ID-enrollment-style selfie capture with basic liveness (blink/turn/multi-frame) to deter spoofing | Customer | Mobile | No | High | Front camera + on-device face detection | Advanced anti-spoofing (separate add-on) | Basic liveness can be fooled by sophisticated attacks |  | 26 |  | Advanced presentation-attack detection is an upsell
5 | 2 | Face match | ID-Photo vs Selfie Face Match | Extract face embeddings from the ID photo and selfie on-device and compare similarity against a tuned threshold | Customer | Mobile | No | High | On-device face embedding available; tuning data accessible | Cloud face-recognition services | False rejects on poor ID photos — needs tuning + fallback |  | 40 |  | Biggest accuracy risk; dedicated threshold tuning time
6 | 2 | Flow | Result Handling, Retries & Fallback | Manage pass/fail outcomes, retry limits, clear error states, and an agreed manual-review fallback for legitimate edge cases | Customer | Mobile | Partial | Medium | Manual fallback policy agreed with client | Live human review desk (client-operated) | Fallback policy undefined blocks genuine users |  | 18 |  | Manual fallback policy must be agreed with client
7 | 2 | Privacy | Secure Handling & Deletion of Biometrics | Process ID/selfie/embeddings in secure storage and delete them immediately after the pass/fail decision | Customer | Mobile | Partial | Medium | Secure storage APIs available | Long-term document retention | Residual files if deletion not enforced |  | 16 |  | Backend never receives raw images or biometrics
8 | 2 | Gating | Verification Status & Activation Gate | Persist the verification result and gate first-time device activation on a successful 18+ verification | Customer | Both | Yes | Low | Backend stores age_verified flag | Per-session re-verification | Flag tampering if not server-authoritative |  | 12 |  | Only age_verified (+ timestamp/method) is stored
Subtotal
Exit Criteria | - Valid 18+ ID with a matching selfie → verification passes - Under-18 ID or mismatched selfie → verification blocked with clear message - Poor-quality captures → guided retry within retry limits - All ID/selfie/biometric data deleted after the decision - Only an age_verified flag stored in the backend - First-time device activation is gated on successful verification
🟥 PHASE 3 — PROXIMITY LOCK/UNLOCK & PRODUCTION HARDENING
Goal | Deliver secure lock/unlock control and proximity-based auto-lock, validate against real firmware, harden, and launch on both app stores.
Client framing | This phase delivers: • First-time unlock after successful verification • Authenticated lock/unlock over BLE • Proximity monitoring + auto-lock when the phone leaves range • Correct background behaviour on iOS & Android • Push notifications (lock status, low battery) • Joint firmware integration testing on real hardware • Full E2E QA, security review, and store submission
1 | 3 | Activation | First-Time Unlock (Activation) | After successful age verification, allow the user to activate and unlock the device for the first time | Customer | Mobile | Partial | Medium | Verification flag available; device paired | Activation without verification | Activation race conditions |  | 16 |  | Activation impossible until age_verified is true
2 | 3 | Control | Authenticated Lock/Unlock over BLE | Send authenticated lock/unlock commands via the BLE characteristic; reflect device-reported lock state in the app | Customer | Mobile | Partial | High | Firmware implements the lock command + session auth | Lock control without a paired phone | Replay/spoofed commands if auth weak |  | 24 |  | Only the bonded, verified user's app can command
3 | 3 | Proximity | Proximity Monitor & Auto-Lock on Range Loss | Monitor BLE connection/RSSI and auto-lock when the phone leaves range; firmware also self-locks on link loss (dead-man) | Customer | Both | Partial | High | Firmware dead-man auto-lock implemented per spec | Precise distance/geofencing | RSSI is noisy — thresholds need tuning |  | 38 |  | Device-enforced lock is the safety guarantee, not app-only
4 | 3 | Background | Background BLE Behaviour (iOS & Android) | Ensure proximity monitoring and auto-lock work when the app is backgrounded or the phone is locked, within OS limits | Customer | Mobile | No | High | OS background BLE modes sufficient | Guaranteed instant background wake on all OEMs | iOS/Android background BLE restrictions differ |  | 32 |  | Behaviour and limits documented for the client
5 | 3 | Push | Push Notifications | Notify the user of relevant events: device locked/unlocked, low battery, out-of-range auto-lock | Customer | Both | Yes | Medium | FCM/APNs configured (Phase 0) | SMS notifications | Delivery reliability across platforms |  | 16 |  | Frequency tuned to avoid spam
6 | 3 | Integration | Joint Firmware Integration Testing | Integrate and test the app against real firmware on a physical device: pairing, lock/unlock, auto-lock, battery, edge cases | Admin | Both | Partial | High | Physical device + firmware available by ~week 6 | Firmware bug-fixing (client team) | Firmware delays compress this window |  | 24 |  | Joint testing with the client firmware team
7 | 3 | QA | E2E QA, Edge Cases & Security Review | Full end-to-end testing across the verification, pairing, and lock/unlock flows; security review of auth, storage, and data deletion | Admin | Both | Partial | High | Test devices and sample IDs available | Third-party formal pen-test | Late-found defects near launch |  | 24 |  | Includes the verification accuracy test matrix
8 | 3 | Release | App Store Submission (iOS & Android) | Prepare store listings, assets, privacy disclosures, and submit to the App Store and Google Play | Admin | Both | No | Medium | Developer accounts and store assets ready | Ongoing ASO/marketing | Store review rejection (age-restricted product policy) |  | 16 |  | Age-restricted product policies must be reviewed early
Subtotal
Exit Criteria | - Verified user can lock and unlock the device while in BLE range - Device auto-locks when the phone leaves range (firmware + app) - Proximity behaviour works when the app is backgrounded - Push notifications delivered for lock status and low battery - App validated against real firmware on a physical device - Passes E2E QA + security review - Submitted and live on the App Store and Google Play
|  |  | CORE TOTAL (Phases 0–3) | [8 empty] | 83.5 | 668
Negotiation / Risk Buffer (12%)
GRAND TOTAL (Core + Buffer)
➕ ADD-ONS / UPSELL (OUT OF BASE SCOPE)
Goal | Optional modules presented as add-ons to the core 4-phase delivery.
Client framing | Each item below is quoted separately and is not included in the base 2-month scope.
1 | E) | Admin | Admin Web Panel | Web dashboard for device fleet management, verification audit log, and user management | Admin | Web | Yes | High | Backend exposes admin APIs | — | Standalone product — significant scope |  | 120 |  | Recommended for operations at scale
2 | E) | Analytics | Analytics & Crash Reporting | Integrate analytics and crash reporting (e.g. Firebase/Sentry) for usage and stability insight | Admin | Both | Partial | Low | Analytics SDK and account available | Custom BI dashboards | — |  | 24 |  | Low effort, high operational value
3 | E) | Firmware | Firmware Development | Develop the device firmware on the YC1012_JD + Cortex-M0+ (BLE service, lock/unlock, dead-man auto-lock) | Admin | Both | No | High | Hardware toolchain and access provided | — | Embedded scope — separate estimate |  | 0 |  | Quoted separately if client wants us to build firmware
4 | E) | Security | Advanced Liveness / Anti-Spoofing | Presentation-attack detection to harden the selfie step against photo/video/mask spoofing | Customer | Mobile | No | High | Suitable on-device PAD model available | — | Accuracy/UX tuning intensive |  | 60 |  | Strengthens the verification step
Subtotal