## V2-Master Scope
SN | Phase | Module | Feature Name | Feature Description (Client-Friendly) | User Roles | Platform (Mobile/Web/Both) | ERP Dependency (Yes/Partial/No) | Complexity (Low/Medium/High) | Assumptions | Explicit Exclusions | Risk Note | Effort (Person-Days) | Est. Hours | Cost | Notes / Negotiation Buffer
| 🟦 PHASE 0 — FOUNDATION, ARCHITECTURE & INTEGRATION | [14 empty] | Hourly Rate
| Goal | Establish a secure, scalable, and controlled integration layer between the Mobile App and Odoo ERP. This phase sets up all infrastructure, authentication, license validation, role-based access, Elasticsearch, and API security before any customer-facing functionality is built.
Client framing:
1 | Phase 0 | Architecture | System Architecture Design | Define full mobile–middleware–Odoo architecture including API contracts, data flow diagrams, and integration blueprint for all phases | Admin | Backend | Yes | High | Odoo API access available and documented | Infrastructure procurement / hosting | API limitations discovered late |  | 126 |  | Architecture doc must be approved before Phase 1 begins
2 | Phase 0 | Middleware | Odoo API Integration Layer | Build and configure the middleware API layer that connects the mobile app to Odoo. All data (products, orders, customers, invoices) flows through this layer | All | Backend | Yes | High | Odoo version and modules confirmed | Direct DB access to Odoo | Odoo API rate limits or missing endpoints |  | 60 |  | All future phases depend on this layer being stable
3 | Phase 0 | Auth | Authentication APIs — JWT & Session Management | Build login, token generation, token refresh, logout, and session expiry APIs. Secure JWT lifecycle with defined inactivity timeout | Customer | Backend | Yes | High | OAuth/JWT standard supported | SSO / third-party identity providers | Token expiry edge cases; concurrent session conflicts |  | 34 |  | Session timeout duration to be agreed with client
4 | Phase 0 | Auth | Role-Based Access Control (RBAC) | Enforce partner-level data isolation. Retailer vs Wholesaler roles determine what pricing, products, and data each customer can access | Admin / Customer | Backend | Yes | High | Customer types (Retailer/Wholesaler) defined in Odoo | Multi-company Odoo setup | Data leakage between customer types if misconfigured |  | 26 |  | Roles must be configured in Odoo before testing
5 | Phase 0 | Compliance | License Validation Engine | Build the core license validation service. Validates: license existence, admin verification status, and expiry date. Called at login, product view, cart add, and order confirm | Customer | Backend | Yes | High | Customer Licenses module active in Odoo; license data is clean | Government-issued license verification API | Expiry timing conflicts; license data inconsistency in Odoo |  | 46 |  | This engine is called by Phase 1, 2, and 3 — must be rock solid
6 | Phase 0 | Compliance | License Enforcement Logic in Odoo | Configure Odoo-side rules that block or restrict access when license conditions are not met. Enforces the 7-scenario product visibility matrix at the API response level | Admin | Backend | Yes | High | Odoo customization is allowed; Customer Licenses module available | License issuance workflow | Role conflict between license types |  | 34 |  | Visibility matrix (price/stock hidden) must be enforced here, not only in the app
7 | Phase 0 | Security | HTTPS + API Security Hardening | Enforce HTTPS across all endpoints, implement API key protection, token validation on every request, rate limiting, and input sanitisation | All | Backend | Partial | Medium | SSL certificate ready; infrastructure supports HTTPS | Firewall / WAF infrastructure | Misconfigured SSL; API key leakage |  | 20 |  | Penetration testing not included in this phase — flagged for Phase 3
8 | Phase 0 | Search Infra | Elasticsearch Infrastructure Setup | Provision Elasticsearch cluster, configure index mappings for products (name, SKU, category, barcode, variants), and set up initial sync pipeline from Odoo product catalog | Admin | Backend | Yes | High | Elasticsearch hosting available (cloud or self-hosted) | Elasticsearch licensing cost | Index schema design requires iteration; large catalog may need phased indexing |  | 40 |  | Required before Phase 2 search features can be built
9 | Phase 0 | Search Infra | Odoo → Elasticsearch Sync Pipeline | Build real-time or near-real-time sync so that any product added, updated, or deactivated in Odoo is automatically reflected in Elasticsearch index | Admin | Backend | Yes | High | Odoo webhook or scheduled sync available | Manual indexing | Sync lag; partial failure on bulk updates |  | 24 |  | Critical for search accuracy — stale index = wrong search results
10 | Phase 0 | DevOps | Environment Setup & CI/CD Pipeline | Set up Development, Staging, and Production environments. Configure CI/CD pipeline for automated build, test, and deployment | Admin | Backend | No | Medium | Cloud infrastructure provided by client or agreed vendor | Ongoing hosting cost management | Deployment mismatches between environments |  | 18 |  | Staging must mirror production config exactly
[11 empty] | Total Estimated Hours | 0 | 428 | 0
| Exit Criteria | - System architecture document approved by all stakeholders
- Middleware API layer live and returning correct Odoo data
- JWT authentication working end-to-end (login, refresh, logout, expiry)
- RBAC correctly isolates Retailer vs Wholesaler data
- License validation engine tested against all 7 visibility scenarios
- Elasticsearch cluster live with product index fully synced from Odoo
- Real-time Odoo → Elasticsearch sync confirmed working
- All endpoints secured (HTTPS, token validation, rate limiting)
- Dev / Staging / Production environments configured and verified
🟩 PHASE 1 — CUSTOMER ONBOARDING, IDENTITY & COMPLIANCE
| Goal | Enable business customers to register, submit verification documents, receive portal access, log in, and have full compliance rules enforced before they can place any order. This phase covers the complete customer lifecycle from registration to verified, active account.
| Client framing | This phase delivers: • Full business registration form with document uploads (EIN, licenses, business picture) • Automatic Helpdesk ticket creation in Odoo on every registration submission • Portal access grant + password setup flow (see TBD rows below) • Secure login with session management and password reset • Read-only customer profile (all edits are admin-only in Odoo) • Customer blocking check (due payment, check bounce, account suspension) • Credit limit enforcement before any order can be placed • Age verification popup (21+) for restricted product categories
1 | Phase 1 | Registration | Customer Registration Form — UI | Mobile registration form collecting: Business Name, Email, Phone Number, EIN Number. Validated fields with format checks (email, phone, EIN). Required fields enforced before submission | Customer | Mobile | Yes | Medium | Registration form mirrors existing NepaWholesale website flow | Social login / OAuth registration | Field validation rules for EIN format must be confirmed with client |  | 22 |  | Form fields must exactly match Odoo contact record fields
2 | Phase 1 | Registration | Document Upload — Business Picture & Licenses | Allow customers to upload: Business picture/image, Resale or Tax Resale Certificate, and additional license documents (JPG, PNG, PDF). File type and size validation enforced | Customer | Mobile | Yes | Medium | Odoo supports file attachment on contact/ticket records; file size limit to be defined | Document scanning / OCR | Large file uploads on slow mobile connections; storage management in Odoo |  | 20 |  | Max file size and allowed types to be agreed with client
3 | Phase 1 | Registration | Helpdesk Ticket Auto-Creation on Registration | On form submission, automatically create a Helpdesk ticket in Odoo containing: Business Name, Email, Phone, EIN, source (app), and all attached verification documents | Admin | Backend | Yes | High | Odoo Helpdesk module is active and accessible via API | Manual ticket creation | Ticket duplication if user submits form twice |  | 18
4 | Phase 1 | Registration | Customer Record Creation in Odoo | Create a customer/contact record in Odoo upon registration. Store all submitted business information. Attach uploaded documents to the record | Admin | Backend | Yes | High | Odoo contacts API available and writable | Third-party CRM creation | Odoo field mapping must be pre-agreed to avoid data loss |  | 26 |  | Customer record is the single source of truth for all subsequent operations
5 | Phase 1 | Registration | Duplicate Detection & Flagging | Before creating a new customer record, check for existing duplicates using: Email, Phone Number, Business Name, and EIN Number. Duplicate found = block creation or flag for manual admin review | Admin | Backend | Yes | Medium | Odoo has searchable partner fields | Automated duplicate merge | Partial match logic (e.g. same EIN, different email) needs defined rules |  | 16 |  | Duplicate rules must be defined with client before development
6 | Phase 1 | Auth — TBD | Password Setup — Admin Assigns Credentials (Option A) | Admin creates login credentials in Odoo after verifying the customer. Credentials (email + generated password) are shared with the customer via email notification | Admin / Customer | Backend | Yes | TBD | Admin has access to set portal credentials in Odoo |  | Credential sharing security; customer receiving wrong password |  | 0 |  | ⚠️ TBD — Client must decide between Option A (admin assigns) and Option B (customer sets own). Effort = 0 until decided
7 | Phase 1 | Auth — TBD | Password Setup — Customer Sets Own via Email Link (Option B) | After customer record and portal access are created in Odoo, system sends a password-setup email. Customer clicks link and sets their own password. Same credentials used for portal and mobile app | Customer | Mobile + Backend | Yes | TBD | Odoo portal invitation email flow is available |  | Email deliverability; link expiry handling |  | 0 |  | ⚠️ TBD — Client must decide between Option A and Option B. These are mutually exclusive. Effort = 0 until decided
8 | Phase 1 | Auth | Portal Access Grant | After customer record is created, automatically grant portal access in Odoo so the customer can log in to both the website portal and the mobile app with the same identity | Admin | Backend | Yes | High | Odoo portal access API is available | Manual access grant process | Portal access granted before admin verification is complete — timing must be defined |  | 24 |  | Confirm with client: is portal access immediate on submission, or only after admin approval?
9 | Phase 1 | Auth | Customer Login Screen | Mobile login screen accepting Email (Username) and Password. Authenticates via Odoo API. Only verified + active customers can log in. Pending/Rejected status = blocked with appropriate message | Customer | Mobile | Yes | Medium | Odoo authentication API returns correct status codes | Biometric login (Face ID/fingerprint) | UX iterations on error messaging |  | 18 |  | Error messages must distinguish: wrong credentials vs unverified account vs blocked account
10 | Phase 1 | Auth | Session Token Management | Generate secure session token on successful login. Token used for all subsequent API calls. Session expires after defined inactivity period. Token invalidated on logout | Customer | Backend | Yes | High | Inactivity timeout duration agreed with client | Concurrent multi-device sessions | Token refresh race conditions |  | 18 |  | Inactivity timeout value to be set by client (recommended: 30 minutes)
11 | Phase 1 | Auth | Password Reset via Email | Customer can request password reset from login screen. System sends email with secure reset link. Link updates password in Odoo ERP. Expired/used links handled gracefully | Customer | Mobile + Backend | Yes | Medium | Odoo email server configured; reset flow available via API | SMS-based reset | Reset link expiry window to be defined |  | 14
12 | Phase 1 | Auth | Logout & Session Invalidation | Customer can log out from any screen. On logout: session token is invalidated in backend, customer is redirected to login screen, no cached sensitive data retained | Customer | Mobile | Yes | Low | Token invalidation endpoint available | Remote logout from admin |  |  | 8
13 | Phase 1 | Profile | Read-Only Customer Profile View | Customer can view their profile (Business Name, Email, Phone, Customer Type, Assigned Price List, License Status). All fields are read-only. No edit capability in the app — all updates admin-only in Odoo | Customer | Mobile | Yes | Low | Customer profile data available via Odoo API | Profile editing in app | Displaying sensitive fields like EIN — confirm what is shown |  | 12 |  | Clearly communicate to customer that profile changes must be requested via support
14 | Phase 1 | Profile | License Status Page | Dedicated screen showing all customer licenses: License Type, License Number, Expiry Date, Verification Status (Verified / Pending / Expired / Missing). Clear messaging per status | Customer | Mobile | Yes | Medium | Customer Licenses module data accessible via API | License renewal from app |  |  | 18 |  | Customer must be able to see exactly which licenses are blocking their access
15 | Phase 1 | Profile | License Document Re-Upload from App | Customer can upload a renewed or additional license document directly from the License Status page. Uploaded document is attached to their Odoo customer record and triggers a review/notification to admin. License status remains restricted until admin verifies the new document. Supported file types: JPG, PNG, PDF. File size validation enforced | Customer | Mobile | Yes | Medium | Odoo supports file attachment on customer record via API; admin notification mechanism available (email or Helpdesk ticket) | Automated license renewal with government APIs | Customer may upload incorrect document — admin review step is mandatory before status changes |  | 16 |  | Critical gap identified in cross-check: without this, customers with expired licenses have no self-service path to renew — they must contact admin externally
16 | Phase 1 | Compliance | Customer Blocking System Check | Before allowing login or order placement, check if customer account is blocked in Odoo (reasons: due payment, check bounce, payment mistake). Blocked customers see: 'Your account is currently suspended. Reason: [X]. Please contact support.' Auto-unblock date respected | Customer | Backend | Yes | High | nepa_block_partner module active in Odoo | Manual block override from app | Block reason must be returned by API — confirm field availability in Odoo |  | 24 |  | Block check must occur at: login, cart checkout, and order confirmation
17 | Phase 1 | Compliance | Credit Limit Enforcement | Before order placement, check customer's remaining credit limit (credit limit amount minus total due and unreconciled payments). If insufficient, block order with message: 'Your credit limit has been exceeded. Please contact support.' Display current credit balance in account section | Customer | Backend | Yes | High | nepa_customer_credit_limit module active; credit limit field available via API | Credit limit top-up from app | Real-time credit calculation requires accurate Odoo accounting data |  | 26 |  | Credit limit check must occur at both cart checkout and order confirmation — not just at login
18 | Phase 1 | Compliance | Age Verification Popup (21+) | Display age verification popup before showing or allowing purchase of age-restricted products (tobacco, alcohol, cigars). Customer must confirm they are 21+ before proceeding. Confirmation persists for session | Customer | Mobile | Yes | Medium | Age-restricted product flag available on Odoo product record | ID document verification | Session-based vs persistent confirmation — confirm with client |  | 12 |  | Popup must appear when browsing AND when adding to cart for restricted products
[10 empty] | Total Working Day |  | 0 | 292 | 0
| Exit Criteria | - Registration form submits successfully and creates Odoo record + Helpdesk ticket
- All uploaded documents attached to correct Odoo records
- Duplicate detection correctly flags or blocks duplicate registrations
- Portal access granted and password setup email received (whichever flow client selects)
- Login works for verified + active customers only; blocked/pending accounts correctly rejected
- Session token generated, refreshed, and invalidated correctly
- Password reset flow works end-to-end (email → link → Odoo update)
- Customer profile displays correctly and is fully read-only
- License Status page accurately reflects all license states from Odoo
- Blocked customers cannot log in or place orders; correct reason message shown
- Credit limit check blocks orders when limit is exceeded
- Age verification popup appears and persists correctly for restricted products
🟨 PHASE 2 — PRODUCT CATALOG, STORE MANAGEMENT, SEARCH & PROMOTIONS
| Goal | Deliver the complete product discovery experience: multi-store selection, product browsing with full compliance enforcement (state, country, license, age, ban list), Elasticsearch-powered search, dynamic promotional sections, and wishlist. Every product a customer sees, and every price they view, must be fully compliant with their license and location.
| Client framing | This phase delivers: • Multi-store selection (8+ stores) with per-store inventory and pricing • Full product visibility matrix: price and stock hidden when licenses are invalid • State-based and country-level product restriction enforcement • Product ban list with customer-level exceptions • Elasticsearch search: barcode scanner, voice search, auto-suggestions, filters • Dynamic sections: Featured, Best Selling, New Arrivals, Trending, Recommended • Promotional banners and discount/offer engine synced from Odoo • Wishlist / Favorites for future purchase planning
1 | Phase 2 | Store | Multi-Store Selection Screen | After login, customer selects a store (warehouse) from the list of 8+ stores configured in Odoo. Store list fetched from Odoo. Selection persists for the session. Store name and basic info displayed | Customer | Mobile | Yes | Medium | 8+ stores configured in Odoo warehouses; store API available | In-store POS integration | Store list must be live from Odoo — no hardcoding |  | 18 |  | Store selection screen shown immediately after login, before any product browsing
2 | Phase 2 | Store | Default Store Assignment | Optionally assign a default store to a customer based on: customer location, customer preference, or admin configuration in Odoo. Customer can still manually switch stores at any time | Customer / Admin | Backend | Yes | Medium | Customer location or preference stored in Odoo | Geo-location-based auto-selection | Default store assignment logic must be defined by client |  | 14 |  | If no default is set, customer must manually select store on every login
3 | Phase 2 | Store | Store Switching with Cart Clear Warning | Customer can switch stores from header or menu at any time. On switch: system warns 'Switching stores will clear your current cart.' Cart is cleared. Product listings and inventory refresh for new store | Customer | Mobile | Yes | Medium | Store switch triggers warehouse change in active session | Cart transfer between stores | UX of warning modal must be clear and non-dismissible by accident |  | 16
4 | Phase 2 | Store | Store Locator with Map View | Dedicated Store Locator screen showing all store locations on Google Maps / Apple Maps. Each pin shows: Store Name, Address, Opening Hours, and Contact Information | Customer | Mobile | Partial | Medium | Store location data (address, hours, contact) available in Odoo; Google Maps API key available | Real-time stock check from map | Google Maps API billing — client must provide API key |  | 20
5 | Phase 2 | Product | Product Listing — Per Store & Per Customer | Display products available in the selected store only. Products not stocked in the selected warehouse are hidden or shown as Out of Stock. Category-based browsing with filters | Customer | Both | Yes | Medium | Product-warehouse mapping available in Odoo; product data is structured | 3D product images | Large catalog performance — pagination/lazy loading required |  | 26
6 | Phase 2 | Product | Product Detail Page | Full product detail view showing: Product Name, Image Gallery (with zoom), Price (from customer pricelist), Description and Specifications, Available Variants (size, flavor, color), Stock Availability in selected store, License Requirement Warning (if applicable), Related/Recommended Products, Add to Cart button (disabled if restricted) | Customer | Both | Yes | Medium | Product images available; variant data structured in Odoo | AR product view | Image load performance on slow connections |  | 26 |  | 'Add to Cart' button must be disabled — not hidden — when restrictions apply, with tooltip explanation
7 | Phase 2 | Product | Product Image Gallery & Zoom Viewer | Swipeable image gallery on product detail page with pinch-to-zoom functionality. Multiple images per product supported | Customer | Mobile | Partial | Low | Multiple product images available in Odoo | 360° product view | Image resolution and file size management |  | 6
8 | Phase 2 | Pricing | Customer-Specific Pricing (Pricelist Engine) | Retrieve and display prices according to customer's assigned Odoo pricelist. Retailer customers see: Delivery and Pick Up prices. Wholesaler customers see: Jobber and Wholesaler prices. No cross-pricelist visibility | Customer | Backend | Yes | High | Odoo pricelists configured per customer type; API returns correct pricelist prices | Pricelist redesign during development | Price sync timing — cache must invalidate on pricelist change |  | 38 |  | Customer must ONLY see their own pricelist — never another customer type's pricing
9 | Phase 2 | Compliance | Product Visibility Matrix — License Enforcement | Enforce the 7-scenario product visibility matrix: 1. Valid resale + non-sensitive = show price & stock 2. Missing resale + non-sensitive = hide price & stock + message 3. Expired resale + non-sensitive = hide price & stock + message 4. Valid resale + valid sensitive license = show price & stock 5. Valid resale + missing sensitive license = hide price & stock + message 6. Valid resale + expired sensitive license = hide price & stock + message 7. Missing resale + sensitive product = hide price & stock + message | Customer | Both | Yes | High | Customer Licenses module in Odoo returns license type, status, expiry per customer | Government license validation API | License status must be checked in real-time — caching must have short TTL |  | 46 |  | Products are ALWAYS visible. Only price and stock are hidden. This is a hard business rule
10 | Phase 2 | Compliance | License Status Messaging — In-App | Display clear, contextual messages when price/stock are hidden due to license issues: • 'Your resale license is missing. Please upload a valid resale license to view prices and stock.' • 'Your resale license has expired. Please renew your license to view prices and stock.' • 'This product requires an additional tobacco-related license. Please upload a valid license to continue.' • 'Your required category license has expired. Please renew it to view prices and stock.' | Customer | Mobile | Yes | Medium | License status and type returned correctly by validation engine | In-app license upload | Message copy to be approved by client before development |  | 12
11 | Phase 2 | Compliance | State-Based Product Restriction Enforcement | Before displaying any product, validate against the customer's state (retrieved from Odoo customer profile). Products or variants restricted in that state are: not displayed, OR the restricted variant is hidden. Restriction rules configured in Odoo | Customer | Backend | Yes | High | Customer state stored in Odoo profile; product state restriction rules configured in Odoo | Real-time government regulatory API | Restriction rules may change — must be configurable in Odoo, not hardcoded in app |  | 28 |  | Customer's state is verified during onboarding and stored in Odoo — app reads it, does not collect it
12 | Phase 2 | Compliance | Country-Level Product Restriction Enforcement | Enforce allowed_country_ids on products — only display products that are permitted in the customer's country. Country data retrieved from Odoo customer profile | Customer | Backend | Yes | Medium | allowed_country_ids configured on products in Odoo; sale_allowed_countries module active |  | Country-level rules must not conflict with state-level rules |  | 16 |  | Runs in addition to state-level checks — both must pass
13 | Phase 2 | Compliance | Product Ban List with Customer Exceptions | Apply product ban rules configured in Odoo (nepa_product_ban_list): bans by country, state, customer type (retail/wholesale/all), applied to categories, product templates, or specific variants. Individual customers with special exceptions can bypass applicable bans | Customer | Backend | Yes | High | nepa_product_ban_list module active in Odoo; customer-level exception fields available | Ban management from mobile app | Exception logic must be checked BEFORE applying ban — order of operations critical |  | 32 |  | Customer-specific exceptions must be checked first; if exception exists, do not hide the product
14 | Phase 2 | Search | Elasticsearch Product Search | Fast keyword search powered by Elasticsearch. Supports: product name search, SKU/product code, category-based search, keyword search, partial word matching with auto-suggestions, and relevance ranking based on search terms | Customer | Mobile | Yes | High | Elasticsearch cluster live (Phase 0); product index synced from Odoo | Semantic / AI-powered search | Search result quality depends on index quality — catalog data must be clean |  | 38 |  | Search results must respect the same product visibility rules (license, state, store)
15 | Phase 2 | Search | Barcode / SKU Scanner | In-app barcode scanner (camera-based) that searches for products by barcode. Must search across ALL barcodes assigned to a product (multi-barcode support via nepa_multibarcodes_product), not just the primary barcode | Customer | Mobile | Partial | Medium | Multi-barcode fields available on Odoo products; camera permission handled | External barcode hardware | Different barcode formats (EAN-13, UPC-A, QR) must all be supported |  | 16
16 | Phase 2 | Search | Search History & Auto-Suggestions | While typing in search bar, display: auto-suggestions for matching products, suggested categories, recent search history (stored locally per session). Suggestions powered by Elasticsearch partial matching | Customer | Mobile | Yes | Medium | Elasticsearch supports partial matching and suggestions | Cross-device search history sync | Suggestion relevance tuning may require iteration post-launch |  | 16
17 | Phase 2 | Search | Voice Search | Customer can tap microphone icon and speak a product name or keyword. Voice input converted to text and used as search query in Elasticsearch | Customer | Mobile | Partial | TBD | Device microphone permission; speech-to-text library available | Multi-language voice search | Voice recognition accuracy for product names / industry terms |  | 0 |  | ⚠️ TBD — Voice search accuracy for wholesale product names is uncertain. Recommend confirming priority with client before scoping effort
18 | Phase 2 | Search | Search Filters & Sorting | After search results are returned, allow customers to refine by: Category, Price range, Product variants, Availability in selected store. Sorting options: Relevance, Price (low-high / high-low), Name (A-Z) | Customer | Mobile | Yes | Medium | Filter attributes available in Elasticsearch index | Saved filter presets | Filter combinations must be tested for performance |  | 16
19 | Phase 2 | Promotions | Dynamic Product Sections — Home Screen | Display configurable product sections on the home screen, managed from Odoo: Featured Products, Best Selling Products, Relevant / Recommended Products, New Arrivals, Trending Products, Category-based highlights. Sections update dynamically without requiring app update | Customer | Mobile | Yes | High | Odoo CMS or product tagging supports section configuration; API returns section data | Manual curation from app | Section configuration API must be designed to be flexible for future section types |  | 24 |  | All section content managed in Odoo — no hardcoding of products in the app
20 | Phase 2 | Promotions | Promotional Banners — Home & Category Screens | Display promotional banners on home screen and category screens. Banners show: current promotions, special deals, and seasonal campaigns. Banners managed from Odoo or backend admin. Support for image banners with tap-through links | Customer | Mobile | Yes | Medium | Banner images and links stored/managed in Odoo or linked CMS | Video banners | Banner image size/format standards must be defined to avoid layout issues |  | 14
21 | Phase 2 | Promotions | Discount & Promotions Engine | Apply all Odoo-configured promotions automatically in the app: discount campaigns, product-specific discounts, category discounts, Buy X Get Y offers, limited-time promotional offers, and pricelist-based promotions. Pricing shown to customer already reflects applicable discounts | Customer | Backend | Yes | High | Odoo promotions and pricelists fully configured; promotion API returns correct prices | Building a custom discount engine | Promotion stacking rules must be defined — can multiple promotions apply to one order? |  | 36 |  | Promotions are Odoo-managed — app applies and displays, does not calculate independently
22 | Phase 2 | Promotions | Coupon & Promo Code Validation with Per-Customer Limits | Customers can enter coupon/promo codes at cart stage. Validate code against Odoo. Respect per-customer usage limits (coupon_per_partner / customer_loyalty_limits modules). Error message if: code invalid, expired, or usage limit reached | Customer | Both | Yes | High | coupon_per_partner module active; coupon limits configured in Odoo | Coupon creation from app | Limit enforcement must happen server-side — not only in app UI |  | 20
23 | Phase 2 | Wishlist | Wishlist / Favorites | Customers can save products to a Wishlist/Favorites list for future purchase. Wishlist is stored per customer (in Odoo or middleware). Customer can view, remove, and add-to-cart from wishlist. Wishlist respects all product visibility rules | Customer | Both | Yes | Medium | Wishlist storage solution agreed (Odoo custom model or middleware DB) | Wishlist sharing | Wishlist items must re-validate license/state restrictions when cart is initiated |  | 14
24 | Phase 2 | Product | Product Comparison Feature | Customers can select 2–3 products to compare side-by-side: Price, Variants, Specifications, Stock Availability. Useful for wholesale buyers choosing between similar SKUs | Customer | Mobile | Partial | Medium | Product specification fields structured consistently in Odoo | Comparison across categories | Comparison only meaningful if product specs are standardized — flag risk to client |  | 12
[10 empty] | Total Working Day |  | 0 | 504 | 0
| Exit Criteria | - Store selection screen lists all Odoo-configured stores correctly
- Store switching clears cart and refreshes inventory for new store
- Store Locator map shows all stores with correct info
- Product listing shows only products available in selected store
- Product detail page displays all required fields (gallery, variants, specs, stock, license warning)
- Customer-specific pricing shows correct pricelist — no cross-pricelist leakage
- All 7 product visibility matrix scenarios verified with correct price/stock hiding
- License status messages appear correctly per scenario
- State-based and country-level restrictions correctly hide/show products
- Product ban list applied; customer exceptions bypass bans correctly
- Elasticsearch search returns fast, accurate results across all supported query types
- Barcode scanner finds products using any of their assigned barcodes
- Auto-suggestions appear while typing; search history displayed
- Dynamic product sections load from Odoo config — no hardcoded products
- Promotional banners render correctly on home and category screens
- Discounts and promotions applied correctly at product and cart level
- Coupon per-customer limits enforced server-side
- Wishlist saves, persists, and re-validates restrictions correctly
🟥 PHASE 3 — CART, CHECKOUT, ORDERS, INVOICING, COMMUNICATIONS & SCALE
| Goal | Deliver the complete transactional experience: cart management with all compliance validations, full checkout flow, order tracking, invoicing, financial account view, live chat, push notifications, helpdesk forms, and all performance, governance, and audit requirements. This phase makes the app production-ready.
| Client framing | This phase delivers: • Full cart management with compliance re-validation (license, state, credit limit, block) • Complete checkout: delivery address, delivery method, pickup store, payment, tax summary • Orders created in Odoo with correct warehouse assignment; real-time status sync • Order history with one-tap reorder and full delivery tracking • Invoice listing (all sources), PDF download, payment history, credit balance • Push notifications (order, promo, back-in-stock, abandoned cart, support updates) • Live Chat via Odoo Discuss; custom forms → Helpdesk tickets • Cart activity logging, abandoned cart automation, API caching • Full audit logging, admin reporting dashboard, license expiry alerts • Load testing, performance benchmarking, and full API documentation
1 | Phase 3 | Cart | Cart Management — Add, Update, Remove | Add products to cart, update quantities, remove items. Cart validates product availability in selected store at time of add. Cart displays: product name, variant, quantity, unit price, line total, and cart grand total | Customer | Both | Yes | Medium | Cart stored server-side (Odoo draft order or middleware); product availability real-time | Cross-device cart sync | Quantity changes must re-validate availability in real-time |  | 20
2 | Phase 3 | Cart | Cart Persistence Across Sessions | Cart is saved and restored across sessions. If customer logs out and logs back in, cart items are retained (subject to product availability at time of return) | Customer | Backend | Yes | Medium | Cart stored in Odoo draft order or middleware DB linked to customer |  | Expired session must not lose cart silently — clear notification required |  | 14
3 | Phase 3 | Cart | Cart Compliance Validation (Full Gate Check) | When customer attempts to add any item to cart or proceed to checkout, validate ALL of the following: 1. Product license requirement + customer license validity + expiry 2. State-based product restriction 3. Country-level restriction 4. Product ban list (with customer exception check) 5. Customer account not blocked 6. Customer credit limit sufficient If any check fails: item not added, specific error message shown | Customer | Backend | Yes | High | All validation rules available via middleware license engine (Phase 0) |  | All 6 validation rules must run in sequence — short-circuit on first failure with correct message |  | 38 |  | This is the most critical compliance gate — must be tested exhaustively
4 | Phase 3 | Cart | Cart Activity Logging in Odoo | Log all cart activity (items added, removed, quantity changes, cart abandoned) as footprint records in Odoo. Used for admin reporting, abandoned cart analysis, and audit trail | Admin | Backend | Yes | High | Odoo custom model for cart log available or approved | CRM automation triggers | High-frequency write operations — must be async to not slow cart UX |  | 16
5 | Phase 3 | Cart | Abandoned Cart Detection & Automation | Automatically mark carts as abandoned after a configurable inactivity threshold (e.g., 24 hours). Trigger email notification to customer about abandoned cart. Admin can view abandoned cart report in Odoo | Admin / Customer | Backend | Yes | High | Scheduled job (cron) available; email server configured | SMS abandoned cart reminders | Cron timing precision; email deliverability |  | 16 |  | Threshold duration to be configured by admin — not hardcoded
6 | Phase 3 | Checkout | Delivery Address Selection | At checkout, customer selects a delivery address from their saved addresses (retrieved from Odoo contact record). Address displayed as: Address Line, City, State, Zip, Country. Note: adding or editing addresses is admin-only — read-only in app | Customer | Mobile | Yes | Medium | Customer's saved addresses available via Odoo contacts API | Address editing in app | Customer with no saved addresses — fallback must be defined |  | 12 |  | Confirm with client: what happens if customer has no saved delivery address?
7 | Phase 3 | Checkout | Delivery Method Selection | Customer selects delivery method: Shipping (home/business delivery) or Store Pickup. Available methods fetched from Odoo delivery carrier configuration for the selected warehouse | Customer | Mobile | Yes | Medium | Delivery methods configured per warehouse in Odoo | Real-time delivery cost calculation | Not all delivery methods available for all stores — must filter by warehouse |  | 16
8 | Phase 3 | Checkout | Pickup Store Selection at Checkout | If 'Store Pickup' is selected as delivery method, display list of available pickup locations for the selected warehouse. Each location shows: Name, Address, Opening Hours, Contact Info. Customer selects preferred pickup point | Customer | Mobile | Yes | Medium | Pickup store data (delivery_carrier_pickup_store module) available via Odoo API |  | Pickup locations must match the selected store/warehouse |  | 16
9 | Phase 3 | Checkout | Payment Method Selection (Offline Only) | Display only the payment methods enabled in Odoo ERP for the customer. All payment is offline — no payment gateway integration. Selected payment method is recorded in the Odoo Sales Order. Payment collected by company offline | Customer | Mobile | Yes | Low | Payment methods configured and enabled in Odoo; API returns enabled methods only | Online payment gateway | Only show enabled payment methods — never hardcode |  | 8 |  | Offline payment means: customer selects method, order created, company collects payment physically/by bank transfer
10 | Phase 3 | Checkout | Order Summary with Tax Calculation & Promo Code | Before final order confirmation, display: itemised cart, delivery method and cost, selected payment method, taxes applied, coupon/promo code field and discount applied, and grand total. Customer reviews and confirms | Customer | Mobile | Yes | Medium | Tax rules configured in Odoo; promotion engine returns correct totals | Custom tax display formatting | Tax rules vary by state — must come from Odoo, not be calculated in app |  | 22
11 | Phase 3 | Order | Order Creation in Odoo (Per-Warehouse) | On order confirmation, create a confirmed Sales Order in Odoo assigned to the selected warehouse. Order includes: customer, delivery address, delivery method, payment method, all line items with quantities and prices, tax, and discount | Customer | Backend | Yes | High | Odoo sales order creation API available; warehouse assignment supported | Custom order workflow outside Odoo | Order must fail gracefully — if creation fails, customer notified and cart preserved |  | 34 |  | Single store per order rule enforced — mixed-store cart cannot be submitted
12 | Phase 3 | Order | Order Status Sync — Real-Time | Customer can view current order status in the app. Status synced from Odoo in real-time or near-real-time: Draft → Confirmed → Picked → Shipped → Delivered. Status change triggers push notification | Customer | Both | Yes | High | Odoo order status API or webhook available | Custom workflow stages outside standard Odoo | Status mismatch if Odoo workflow is customised — confirm stage names with client |  | 24
13 | Phase 3 | Order | Order History & One-Tap Reorder | Customer can view full order history: Order Number, Date, Status, Total Amount. Tap to expand: Line Items (product, qty, price), Delivery Tracking, Invoice link. One-tap reorder: pre-fill cart with same items (subject to current availability and compliance validation) | Customer | Both | Yes | Medium | Order history available via Odoo API; re-order respects current stock and compliance | Saved order templates / favourites | Reorder must re-validate license and state restrictions — products may no longer be eligible |  | 26
14 | Phase 3 | Order | Delivery Tracking | Show delivery/shipping status for placed orders: Order Confirmed → Picked → Shipped → Delivered. Display tracking number (if available from carrier). Display estimated delivery date (if provided by Odoo / carrier) | Customer | Mobile | Yes | Medium | Tracking number and status available on Odoo delivery order record | Live carrier tracking API integration (FedEx, UPS, etc.) | Carrier API integration is excluded — tracking number is displayed if present in Odoo |  | 14 |  | Real-time carrier tracking (GPS-level) is out of scope — display tracking number only
15 | Phase 3 | Invoice | Invoice Listing — All Sources | Display all invoices associated with the customer regardless of source: POS, Website, Backend (Odoo). List view showing: Invoice Number, Date, Status (Paid/Outstanding/Overdue), Total Amount | Customer | Both | Yes | High | Unified invoice access via Odoo API across all invoice sources | Custom ledger redesign | Data volume — customers with long history may have hundreds of invoices — pagination required |  | 22
16 | Phase 3 | Invoice | Invoice Detail View | Tap an invoice to see full breakdown: Invoice Number, Date, Due Date, Status, Line Items (product, qty, unit price, subtotal), Tax, Total Amount, Payment Status | Customer | Both | Yes | Medium | Invoice line item data available via Odoo API | Custom invoice layout | Tax line display format must match what customer is accustomed to seeing |  | 12
17 | Phase 3 | Invoice | Invoice PDF Download & Share | Customer can view, download, and share invoice as PDF directly from the app. PDF generated/fetched from Odoo. Sharing via native device share sheet (email, WhatsApp, etc.) | Customer | Mobile | Yes | High | Odoo PDF invoice endpoint available and returns correctly formatted PDF | PDF redesign / custom template | File size management; slow connections may delay PDF load |  | 16
18 | Phase 3 | Invoice | Payment History & Outstanding Invoices | Customer can view their payment history (paid invoices, payment dates, amounts). View outstanding invoices and total amount due. Clear separation between paid and overdue items | Customer | Both | Yes | Medium | Payment records available via Odoo accounting API | Payment initiation from app | Reconciliation logic must be handled in Odoo — app displays only |  | 12
19 | Phase 3 | Invoice | Credit Balance & Remaining Credit Limit Display | Customer can see current credit balance and remaining credit limit in their account/profile section. Shows: Credit Limit, Total Outstanding, Remaining Available Credit. Updates in near-real-time | Customer | Mobile | Yes | Medium | nepa_customer_credit_limit module data accessible via API | Credit top-up request from app | Must reflect accurate Odoo accounting state — stale data causes trust issues |  | 12
20 | Phase 3 | Account | Assigned Sales Representative Display | If customer is linked to a sales representative in Odoo, display their assigned salesperson: Name, Phone Number, Email. Customer can tap to call or email directly | Customer | Mobile | Yes | Low | Salesperson field on Odoo customer record populated | Salesperson chat in-app |  |  | 6
21 | Phase 3 | Live Chat | Odoo Live Chat Integration | In-app Live Chat option where customer can start a real-time conversation with the support team. All chats connected to Odoo Live Chat / Discuss. Support agents receive and respond from Odoo dashboard. Chat history maintained in Odoo for follow-up | Customer | Mobile | Yes | High | Odoo Live Chat module active; API or WebSocket integration available | Third-party chat platform (Intercom, Zendesk) | WebSocket connection stability on mobile networks; chat history sync |  | 34 |  | Conversations appear in Odoo Discuss — support team works entirely within Odoo
22 | Phase 3 | Forms | Custom Forms & Helpdesk Ticket Creation | Support multiple custom forms (inquiries, complaints, support requests, document submissions) configurable from Odoo. Each form submission automatically creates a Helpdesk ticket in Odoo with all submitted data attached. Forms manageable from Odoo without app update | Customer | Mobile | Yes | High | Odoo Helpdesk module active; form configuration API available | Building a custom form builder outside Odoo | Form schema must be dynamic — fetched from Odoo at runtime, not hardcoded |  | 26
23 | Phase 3 | Notifications | Push Notification Engine (FCM / APNs) | Build push notification infrastructure using Firebase Cloud Messaging (Android) and Apple Push Notification Service (iOS). Manage device token registration, renewal, and invalidation. Notification delivery confirmation | Customer | Both | Yes | High | FCM and APNs accounts configured; device token management agreed | SMS fallback notifications | Token expiration and refresh; users who uninstall/reinstall app |  | 30
24 | Phase 3 | Notifications | Order & Delivery Push Notifications | Push notifications triggered on order events: Order Confirmed, Order Picked, Order Shipped, Order Delivered. Each notification includes: order number, status, and deep link to order detail screen | Customer | Both | Yes | Medium | Odoo order status change triggers available (webhook or polling) | Real-time carrier GPS notifications | Trigger reliability from Odoo — must not miss status changes |  | 14
25 | Phase 3 | Notifications | Promotional & Product Push Notifications | Admin can send push notifications for: Promotions and offers, Product back-in-stock alerts, Price drop alerts, New product launches, Seasonal campaigns, Event reminders | Customer / Admin | Both | Yes | Medium | Admin notification management interface (Phase 0 Add-On) or basic Odoo config | Personalised recommendation engine (browsing history analysis, ML-based suggestions) — notification delivery only, not recommendation generation | Notification frequency limits to avoid spam — define max per day/week with client |  | 14
26 | Phase 3 | Notifications | Abandoned Cart & Reminder Push Notifications | Automated push notification sent to customer when cart is abandoned (configurable threshold). Also: incomplete checkout reminders, product reorder reminders based on order history | Customer | Backend | Yes | Medium | Abandoned cart detection running (row 120); push engine live |  | Ensure customer hasn't completed purchase on another channel before sending |  | 10
27 | Phase 3 | Notifications | Support & License Push Notifications | Push notifications for: New response received on Helpdesk ticket, New message in Live Chat conversation, License expiry warning (30 days, 7 days, expired), App update available | Customer | Both | Yes | Medium | Helpdesk and Live Chat events accessible; license expiry data available |  | License expiry notification timing must be configurable by admin |  | 10
28 | Phase 3 | Notifications | In-App Notification Center | Dedicated in-app screen showing all past and current notifications for the customer. Unread count badge on notification icon. Mark as read, mark all as read, delete notifications | Customer | Mobile | Yes | Medium | Notification history stored in middleware or Odoo |  | Notification retention period to be defined (e.g., 90 days) |  | 10
29 | Phase 3 | Performance | API Caching & Cache Invalidation | Implement smart caching for: product listings, pricing, inventory, store list, promotions. Cache invalidation rules: product update in Odoo → cache cleared. Target: API response < 2 seconds under normal load. Cache layer: Redis or equivalent | All | Backend | Yes | High | Cache infrastructure (Redis) available | Offline-mode full browsing | Cache conflicts between cached and live data — short TTL for license/price data |  | 26 |  | Pricing and license data must have SHORT TTL (max 5 min) — never serve stale compliance data
30 | Phase 3 | Governance | Full Audit Logging — All Mobile Actions | Log all significant mobile actions in Odoo audit layer: Login/Logout, Product views, Cart add/remove, Order creation, License check results, Failed compliance gates. Logs include: customer ID, timestamp, action, result | Admin | Backend | Yes | High | Odoo logging hooks available; custom audit model approved | SIEM platform integration | Log storage growth at scale — archiving strategy required |  | 22
31 | Phase 3 | Governance | Admin Reporting Dashboard | Admin-facing dashboard in Odoo showing: Cart activity reports, Order volume and revenue by store, Abandoned cart report, License compliance status across customers, Push notification delivery rates | Admin | Backend | Yes | High | Odoo reporting module available; data models in place | BI platform integration (Tableau, Power BI) | Query performance on large datasets |  | 26
32 | Phase 3 | Governance | License Expiry Alert System | Proactive license expiry notifications: Admin alerted when customers have licenses expiring in 30 days, 7 days, and on expiry day. Customer notified via push notification (row 142). Admin dashboard shows expiry status across all customers | Admin / Customer | Backend | Yes | Medium | License expiry date stored in Odoo; scheduled job available | Government license renewal API | Alert timing precision; must not alert for already-renewed licenses |  | 14
33 | Phase 3 | Performance | Load Optimisation & Stress Testing | Stress test all APIs under simulated peak load. Validate <2 second response time target. Identify and fix bottlenecks. Test concurrent user scenarios (multiple customers browsing, adding to cart, placing orders simultaneously) | All | Backend | No | High | Load testing infrastructure available (e.g., k6, JMeter) | CDN setup | Unexpected scale events; infrastructure scaling costs |  | 22 |  | Conduct before production launch — not optional
34 | Phase 3 | Governance | Offline Behaviour Definition | Define and implement app behaviour when device is offline: Can customer browse cached products? Are cart items saved locally? What happens if connection drops during checkout? Display clear online/offline status indicator | Customer | Mobile | No | TBD | Offline strategy agreed with client | Full offline mode with complete product catalog | Offline product data staleness — compliance checks cannot run offline |  | 0 |  | ⚠️ TBD — Client must define offline behaviour expectations. Offline compliance validation is impossible — this needs a policy decision before development
35 | Phase 3 | Governance | Multi-Language Support | App supports multiple languages. Language selection available in app settings. All UI labels, messages, and product content translated. Language preference stored per customer | Customer | Mobile | Partial | TBD | Translation strings agreed; product content in Odoo supports multiple languages | Automatic machine translation of product descriptions | Odoo product content may only be in English — client must clarify |  | 0 |  | ⚠️ TBD — Client must confirm which languages are required and whether Odoo product data supports them. Effort depends heavily on language count
36 | Phase 3 | Documentation | API Documentation & Deployment Guide | Deliver full technical documentation: API endpoint reference (all routes, params, responses), Odoo integration guide, deployment runbook for Dev/Staging/Production, troubleshooting guide | Admin | Backend | No | Medium | Architecture finalised; all APIs stable | Ongoing documentation maintenance | Scope creep if documentation is requested mid-development — must happen at end |  | 14
[10 empty] | Total Working Day |  | 0 | 628 | 0
| Exit Criteria | - Cart correctly validates all 6 compliance checks (license, state, country, ban, block, credit)
- Cart activity logged in Odoo for all add/remove/abandon events
- Abandoned cart detection and email notification working
- Full checkout flow completed: address → delivery method → pickup store → payment → tax summary → confirm
- Orders created in Odoo with correct warehouse assignment
- One-store-per-order rule enforced — mixed-store cart blocked
- Order history and one-tap reorder working (with re-validation)
- Delivery tracking status displayed and accurate
- Invoice listing shows all invoices from all sources (POS, web, backend)
- Invoice PDF downloads and shares correctly
- Payment history, outstanding invoices, and credit balance display accurately
- Live Chat connects to Odoo Discuss and chat history is retained
- Custom form submissions create Helpdesk tickets with all data attached
- Push notifications delivered correctly for all notification types
- In-app notification centre displays history with read/unread states
- API caching working; cache invalidates correctly on Odoo data change
- Full audit log captured for all significant mobile actions
- Admin reporting dashboard accessible with correct data
- License expiry alerts triggered at correct intervals
- System passes load test with <2 second response time under peak load
- All API documentation delivered and reviewed
➕ ADD-ON MODULE — ADMIN CMS & MOBILE APP MANAGEMENT
| Goal | Module that gives non-technical administrators full control over the app's UI, content, promotions, and push notifications — without requiring developer involvement. Presented as an add-on to the core 4-phase delivery.
| Client framing | This add-on enables: • Non-technical admin to update app theme, layout, menus, and banners without code changes • Create, schedule, and send push notifications from an admin panel • Preview UI changes before they go live to all customers • Manage app versioning and feature rollouts without developer intervention • Access analytics on user behaviour and UI change impact • All changes sync to mobile app in real-time via Odoo API ⚠️ This is a significant standalone product.
1 | Add-On | Admin CMS | App Theme Customisation | Admin can update: App primary and secondary colour palette, fonts, logo, and brand assets. Changes apply to all screens without app store resubmission | Admin | Web (Admin Panel) | Yes | High | Theming framework supports runtime updates | Native OS-level UI components | Theme changes must not break component rendering |  | 26
2 |  | Admin CMS | Navigation Menu Management | Admin can add, remove, reorder, and rename navigation menu items. Changes reflected in app without update | Admin | Web (Admin Panel) | Yes | Medium | Menu config stored in backend and fetched dynamically by app |  | Menu changes go live immediately — need a publish/draft workflow |  | 14
3 |  | Admin CMS | Home Screen Layout Control | Admin can rearrange sections on the home screen: move featured products, categories, banners, and promotional sections. Drag-and-drop layout editor | Admin | Web (Admin Panel) | Yes | High | Layout config API designed in Phase 2 |  | Complex layout engine — recommend scoping separately |  | 30
4 |  | Admin CMS | Product Sections Management | Admin can configure which products appear in Featured, Best Selling, New Arrivals, Trending, and Recommended sections. Set products, sort order, and visibility window per section | Admin | Web (Admin Panel) | Yes | Medium | Product tagging or section config available in Odoo |  |  |  | 20
5 |  | Admin CMS | Promotional Banner Management | Admin can add, edit, remove, and schedule promotional banners. Upload banner images, set tap-through links, and define display period (start date / end date) | Admin | Web (Admin Panel) | Yes | Medium | Banner storage and scheduling available in backend |  |  |  | 20
6 |  | Admin CMS | Button, Icon & Label Text Management | Admin can update text labels on buttons, icons, and UI elements across the app (e.g., rename 'Add to Cart' to 'Add to Order'). Changes applied without app update | Admin | Web (Admin Panel) | Yes | Medium | App uses dynamic string keys fetched from backend |  | Label changes must not exceed UI space constraints — validation needed |  | 20
7 |  | Admin CMS | Custom Page Layouts (About, FAQ, Contact) | Admin can create and edit custom static pages: About Us, FAQ, Contact Us, Terms & Conditions. Rich text editor for content management | Admin | Web (Admin Panel) | Yes | Medium | CMS content API available |  |  |  | 12
8 |  | Admin CMS | Push Notification Management Panel | Admin can: create new push notifications with title, body, image, and deep link; schedule notifications for a future date/time; send to all users, a segment, or specific customers; view delivery and open rate analytics | Admin | Web (Admin Panel) | Yes | High | FCM/APNs infrastructure live (Phase 3); segmentation data available |  | Segmentation logic complexity depends on targeting rules |  | 36
9 |  | Admin CMS | UI Preview Before Publishing | Admin can preview any UI change (theme, layout, banner, menu) on a simulated device screen before pushing to live app. Preview mode does not affect production customers | Admin | Web (Admin Panel) | No | High | Preview infrastructure (e.g., shadow config) available |  | Complex to implement reliably — significant engineering effort |  | 28
10 |  | Admin CMS | App Version Control & Feature Rollout | Admin can manage app versions: push UI updates, features, or content changes to all users or a percentage rollout. Rollback capability if issues are found | Admin | Web (Admin Panel) | No | High | Mobile app supports remote config (e.g., Firebase Remote Config) | App store submissions for native code changes | Remote config only — native code changes still require app store submission |  | 28
11 |  | Admin CMS | Category Display Control (Grid / List View) | Admin controls how product categories are displayed: grid view or list view. Set default view and allow/disallow customer to toggle | Admin / Customer | Web (Admin Panel) | Partial | Low |  |  |  |  | 6
12 |  | Admin CMS | Cart & Checkout Page Layout Control | Admin can configure the layout of cart, checkout, and order confirmation pages: field order, visible/hidden sections, custom messages at checkout | Admin | Web (Admin Panel) | Yes | Medium | Checkout layout config API available |  |  |  | 20
13 |  | Analytics | Analytics Integration — User Behaviour Tracking | Integrate analytics tool (e.g., Firebase Analytics, Mixpanel) to track: conversion rates, drop-off points, most-viewed products, search terms, notification open rates. Reports visible in admin panel | Admin | Web (Admin Panel) | Partial | High | Analytics SDK integrated in mobile app | Custom BI dashboard build | Analytics tool selection and account setup by client |  | 28
14 |  | Analytics | User Feedback Collection on UI Changes | In-app prompt to collect user feedback after significant UI changes. Feedback (rating + comment) stored and viewable in admin panel | Customer / Admin | Both | Partial | Medium |  |  |  |  | 10
| Exit Criteria | - Admin can update theme colours/fonts/logo without code deployment | [7 empty] | Total Working Day |  | 0 | 298 | 0
- Navigation menu changes reflect in app within defined sync time
- Home screen layout changes visible after admin publishes
- Push notifications created, scheduled, and delivered correctly from admin panel
- UI preview mode does not affect production customer experience
- Analytics data visible and accurate in admin dashboard
- All changes sync to app in real-time via Odoo API
| Total Estimated Hours | 2150
| Total Working Days - (all phases) | 0